## Slide 1
Experiential Opportunity:
Preparing for Implementation of a Health Innovation in Clinical Settings
Allison Cole, MD, MPH
Associate Professor, Family Medicine
University of Washington School of Medicine
Director, ITHS Dissemination and Implementation Program
Notes: This experience helps trainees use an implementation planning tool in the context of their own work.

## Slide 2: Goals of the Experiential Learning Opportunity
Learn about the ITHS’ resource: Implementation in Clinical Settings: A Planning Guide for Investigators
Complete a step in the implementation planning process relevant to your intervention and the clinical settings where it will be used
Gain experience in applying Implementation Science principles to a translational research project

## Slide 3: Experiential Learning Process
Review materials (this slideshow & worksheets)
Meet with the ITHS D&I team for orientation & guidance (30 min)
  Please contact NAME/EMAIL, to schedule a time
Complete a planning worksheet for your project
  Choose one:
      Option 1: Understanding your intervention
      Option 2: Operationalizing implementation
Notes: Helpful to provide an overview of the timeline at this point as well.

## Slide 4: Implementation in Clinical Settings: A Planning Guide for Investigators
GOAL:
Help investigators successfully plan implementation of a health intervention or innovation (drug, device, clinical guideline, policy) in clinical settings
  Based on established principles of Implementation Science
  Supported by the ITHS’ Dissemination and Implementation Program
Notes: The goal of the Implementing Health Innovations in Clinical Practice toolkit is to help investigators successfully plan implementation of a health intervention or innovation (drug, device, clinical guideline, program or policy) in clinical settings. The toolkit is based on established principles of implementation science and supported by the ITHS’ Dissemination and Implementation program.

## Slide 5: Who should use the Implementation Guide?
The guide is a good fit if you:
  Have an intervention
  The intervention would be used in clinical settings

## Slide 6: Implementation Planning Exercise Overview
In this modified version of the Guide you will learn about two important steps in the process of planning for implementation
Understanding your intervention
Creating an action plan for one implementation strategy that is appropriate for your intervention and clinical setting

## Slide 7: Understanding your Intervention
The first step in preparing for implementation is to carefully describe your intervention.
This will help you identify the key personnel involved in your intervention and the expected activities and outcomes that will occur.
Focus on the aspects of your intervention that are critical for its success. These are considered the intervention’s core components.
The Guide will guide you through a step-by-step process to examine your intervention

## Slide 8: Understanding your Intervention
Inputs – resources needed to support the intervention. For example, staff, materials, training, existing clinical workflows, funding, equipment
Activities – components of the intervention itself. Activities include both actions to prepare for implementation (e.g. develop new clinical workflow) and actions for implementing and maintaining the intervention (e.g. administering the new treatment)
Short term outcomes – what you expect to occur as a result of the intervention activities. Short term outcomes may reflect modifications or changes in healthcare process (e.g., number of patients contacted) or healthcare service (e.g. number of tests performed)
Long term outcomes – anticipated health outcomes that will occur as a result of the intervention

## Slide 9: Overview of Implementation Strategies
An implementation strategy is a “method or technique used to enhance the adoption, implementation, and sustainability of a clinical program or practice.” (Proctor EK, Powell BJ, McMillen JC 2013 https://doi.org/10.1186/1748-5908-8-139)
There are some implementation strategies that appear to be foundational to implementing interventions in primary care clinical practice. They may be applicable to many clinical settings and across many types of interventions.

## Slide 10: Foundational Implementation Strategies
Assess for readiness | Throughout implementation, assess aspects of a practice or organization to determine its degree of readiness to implement the intervention
Assess for the presence of barriers that may impede implementation | Assess various aspects of a practice or organization to identify barriers that may impede implementation
Attend to Practice or Organization Culture | Identify and respond to the culture of the practice or organization that you are working with (e.g. openness and communication, general leadership support and/or structure).
Conduct Local Planning Discussions | Plan and conduct discussions that include providers or staff and address choosing and testing changes to support implementation of the intervention
Develop and Support Teams that are Implementing the Intervention | Develop and support teams that are implementing the innovation. This can be accomplished through regular check-ins, which give the teams protected time to reflect on the implementation effort, share lessons learned, and support one another’s learning
Conduct educational meetings | Hold meetings targeted toward different stakeholder groups (e.g. providers, administrators, other practice or organizational stakeholders) to teach them about the intervention
Develop or Implement Tools for Quality Monitoring | Develop, test, or introduce quality monitoring tools and teach practices or organizations use of the quality monitoring tools.

## Slide 11: Creating an Action Plan
Outline the elements of each implementation strategy you will use
  Who – Who will deliver it
  What/How – What are the actions or steps; how will it be carried out
  Target of the strategy – Where or to whom is it direct or what is it trying to impact
  Goal or expected outcome
  Timing – When in the project will it be used
  Frequency & Intensity – How often and/or for how long will it be used

## Slide 12: Meet with the ITHS D&I team before choosing and completing your exercise
Notes: Optional to either use group meeting time to help trainees think through which exercise is appropriate for their project, or schedule 1-1 meetings with each trainee after the orientation is over.

## Slide 13: Option 1: Understanding your intervention
Describe your intervention using Worksheet 1 – Intervention

## Slide 14: Option 2: Operationalizing Implementation
Choose one foundational implementation strategy.
Describe how you would use the implementation strategy using Worksheet 2 – Action Plan

## Slide 15: Questions?
NAME, TITLE
EMAIL

## Slide 16
Thank You
ITHS is supported by the National Center For Advancing Translational Sciences of the National Institutes of Health under Award Number UL1 TR002319.
This project was supported by the National Center For Advancing Translational Sciences of the National Institutes of Health under Award Number TL1 TR002318.
The content is solely the responsibility of the authors and does not necessarily represent the official views of the National Institutes of Health.